## Sheet1
project_slug | milestone_order | milestone_title | milestone_description | due_date | due_quarter | department_code | push_number | is_critical | status
bcss-capacity-assurance | 0 | Title card (project start) | Start of the BCSS Capacity Assurance project timeline. | 2025-10-01 | Q4 2025 | PM |  | TRUE | NOT_STARTED
bcss-capacity-assurance | 1 | Delaney meeting outcome | Defined outcome and next steps from the Michael Delaney engagement (documentation, follow-ups, and implications for project path). | 2025-12-31 | Q4 2025 | PM |  | TRUE | NOT_STARTED
bcss-capacity-assurance | 2 | Listening sessions complete (incl. attendee count) | All planned listening sessions completed, attendance captured, and key themes synthesized for next-step planning. | 2025-12-31 | Q4 2025 | CE |  | TRUE | NOT_STARTED
bcss-capacity-assurance | 3 | ICW outfall and Fort Morgan permit clarity | Clarity obtained on ICW outfall and Fort Morgan permitting status, constraints, and implications for capacity and compliance. | 2025-12-31 | Q4 2025 | FR |  | TRUE | NOT_STARTED
bcss-capacity-assurance | 4 | Capacity assurance options drafted | Draft a set of actionable capacity assurance options (cooperative and policy paths), including feasibility, pros/cons, and implementation hooks. | 2026-03-31 | Q1 2026 | PM |  | TRUE | NOT_STARTED
bcss-capacity-assurance | 5 | Citizen reporting soft launch (if greenlit) | Soft-launch a citizen reporting mechanism, contingent on internal greenlight, and validate basic workflow, volume, and response protocol. | 2026-06-30 | Q2 2026 | CE |  | FALSE | NOT_STARTED
bcss-capacity-assurance | 6 | Legal action decision | Decision point on whether to initiate legal action (or hold) based on evidence, leverage, and strategic timing. | 2026-06-30 | Q2 2026 | PM |  | TRUE | NOT_STARTED
bcss-capacity-assurance | 7 | Capacity assurance path chosen | Select the primary path (cooperative, policy, or hybrid) for institutionalizing capacity assurance, with an execution plan. | 2026-06-30 | Q2 2026 | GA |  | TRUE | NOT_STARTED
bcss-capacity-assurance | 8 | WWTP system fixes initiate | Initial system fixes begin (operational and/or capital improvements) aligned with compliance and capacity commitments. | 2026-12-31 | Q4 2026 | FR |  | TRUE | NOT_STARTED
bcss-capacity-assurance | 9 | Transparency or ordinance milestone | Major transparency win and/or ordinance milestone achieved (adoption, implementation step, or equivalent measurable policy outcome). | 2027-03-31 | Q1 2027 | GA |  | TRUE | NOT_STARTED
bcss-capacity-assurance | 10 | Year-to-date compliance audit | Complete YTD compliance audit for 2027 and publish internal findings to inform pressure, comms, and enforcement posture. | 2027-09-30 | Q3 2027 | FR |  | TRUE | NOT_STARTED
bcss-capacity-assurance | 11 | First fixes verified | Verification that first fixes produced measurable improvements (compliance, SSOs, capacity metrics), with documentation. | 2027-12-31 | Q4 2027 | FR |  | TRUE | NOT_STARTED
bcss-capacity-assurance | 12 | Capacity assurance institutionalized | Capacity assurance becomes institutionalized via policy, ordinance, MOU, or standardized utility process with durable enforcement. | 2028-03-31 | Q1 2028 | GA |  | TRUE | NOT_STARTED